## Control Report
DETROIT METROPOLITAN WAYNE COUNTY AIRPORT
P.F.C. QUARTERLY STATUS REPORT
SCHEDULE OF REVENUES AND EXPENDITURES AS OF 09/30/22
TOTAL COLLECTION AUTHORITY: $3,134,966,084
APPROVED
| APPLICATIONS: |  | IMPOSE | USE | TOTAL
|  | Application #1 | 0 | 147914000 | 147914000
|  | Application #2 | 0 | 6443000 | 6443000
|  | Application #3 | 0 | 2098825360 | 2098825360
|  | Application #4 | 0 | 213340000 | 213340000
|  | Application #5 | 0 | 440790156 | 440790156
|  | Application #7 | 0 | 227653568 | 227653568
| TOTAL AUTHORITY |  | 0 | 3134966084 | 3134966084
NOTE: Per Record of Decision dated July 1, 1997 - all PFC projects in Applications #1-5 are approved for Impose & Use.
CURRENT
|  |  |  | QUARTER | CUMULATIVE
|  | PFC Revenue Received |  | 13218608 | 1652772406
|  | Plus: Interest Earned |  | 11514.26 | 73760149
|  | Total PFC Revenue Received |  | 13230122 | 1726532555
|  | Less: PFC Expenditures on Approved Projects |  | 14126316 | 1721449293
Unexpended PFC Balance

## Proj Activity Summ
DETROIT METROPOLITAN WAYNE COUNTY AIRPORT
PFC QUARTERLY STATUS REPORT
PROJECT ACTIVITY SUMMARY AS OF 09/30/22
|  |  | CHARGE | APPROVAL |  |  |  | CURRENT |  | AMOUNT | CURRENT
PROJECT | PROJECTS |  | EFFECTIVE | TO | PROJECT | PROJECT |  | QUARTER | CUMULATIVE | OF USE | ESTIMATED
NUMBER |  |  | DATE | USE DATE | START | COMPLETION |  | EXPENDITURES | EXPENDITURES | APPROVAL | COST
APPLICATION NO. 1
R416 | South Airport Access Road Construction | PAYG | 1993-01-01 | 1992-09-21 | 1991-12-01 | Act | 2005-05-11 | 0 | 28664340 | 38620000 | 38620000
| StormWater Retention & Drainage Facilities Const | PAYG | 1993-01-01 | 1992-09-21 | 1994-08-01 | Act | 2003-12-31 | 0 | 4169572 | 4980000 | 4980000
| Noise Berm Construction | PAYG | 1993-01-01 | 1992-09-21 | 1993-09-01 | Act | 2001-12-01 | 0 | 224927 | 225000 | 225000
| Noise Mitigation Program | PAYG | 1993-01-01 | 1992-09-21 | 1992-05-01 | Act | 2008-03-31 | 0 | 3349999 | 11350000 | 11350000
|  | Cap/Fin/Int | [5 empty] | 126421 | 18274890.07 | 92734000 | 92734000
| Willow Run ALP Update | PAYG | 1993-01-01 | 1992-09-21 | 1993-11-01 | Act | 1995-12-01 | 0 | 5000 | 5000 | 5000
APPLICATION NO. 2
| Land Acquisition and Preliminary | PAYG | 1993-01-01 | 1996-08-02 | 1990-06-01 | Act | 2001-12-31 |  | 2098631 | 3085000 | 3085000
| Design for Fourth Parallel Runway | Cap/Fin/Int | [5 empty] | 0 | 340568 | 3306000 | 3306000
| Perimeter Property Fencing and | PAYG | 1993-01-01 | 1996-08-02 | 1995-03-01 | Act | 2001-12-01 | 0 | 16665 | 52000 | 52000
Removal of Airport Hazard-Willow Run
APPLICATION NO. 3
| Midfield Domestic and International | PAYG | 1993-01-01 | 1997-07-01 | 1997-09-03 | Act | 2002-06-30 | 0 | 240315787 | 240862000 | 240862000
| Terminal Facilities Construction | Cap/Fin/Int | [5 empty] | 9264831 | 763153153 | 1129588360 | 1129588360
| Reconstruction of Existing | PAYG | 1993-01-01 | 1997-07-01 | 1997-09-01 | Act | 2010-03-24 | 0 | 9740830 | 2683000 | 2683000
| Terminals and Concourses | Cap/Fin/Int | [5 empty] | 3097591 | 323132821 | 670725000 | 670725000
| Concourse C Expansion & Domestic | PAYG | 1997-07-01 | 1997-07-01 | 1995-11-17 | Act | 1997-10-31 | 0 | 21693389 | 22967000 | 22967000
| Terminals Facilities Const (Interim Improvement) | Cap/Fin/Int | [5 empty] | 0
| International Passenger Processing | PAYG | 1997-07-01 | 1997-07-01 | 1997-03-24 | Act | 1998-01-31 | 0 | 31800730 | 32000000 | 32000000
Facilities Expansion (Interim Improvement)
APPLICATION NO. 4
A071B | Runway 21C/3C Keel Section Replacement | Cap/Fin/Int | 2029-10-01 | 2000-03-10 | 2001-09-01 | Act | 2004-06-30 | 121957 | 10425853.95 | 16991000 | 16991000
A005A | Runway 4/22 Design and Construction | PAYG | 2029-10-01 | 2000-03-10 | 1998-04-01 | Act | 2005-09-30 |  | 533000 | 533000 | 533000
|  | Cap/Fin/Int | [5 empty] | 590178 | 71986888.28 | 168741000 | 168741000
| Rebuild Outfall Structures at Ponds 3 and 4 | Cap/Fin/Int | 2029-10-01 | 2000-03-10 | 2001-05-01 | Act | 2003-12-31 | 17324 | 1482515.94 | 2413000 | 2413000
| 21C Remote Primary Deicing | PAYG | 2029-10-01 | 2000-03-10 | 1998-09-01 | Act | 1998-12-31 |  | 1817000 | 1817000 | 1817000
|  | Cap/Fin/Int | [5 empty] | 158930 | 13583114.82 | 22141000 | 22141000
A083 | Grade/Pave Taxiway "K" Islands | Cap/Fin/Int | 2029-10-01 | 2000-03-10 | 1998-11-01 | Act | 2010-02-15 | 5056 | 432570.98 | 704000 | 704000
APPLICATION NO. 5
| North Terminal Apron | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2005-09-01 | Act | 2009-12-30 | 0 | 9941028 | 59574000 | 59574000
| McNamara Terminal Phase II Program | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2001-05-01 | Act | 2006-12-31 | 744028 | 126473929 | 277941000 | 277941000
| Third Aircraft Rescue and Firefighting Facility | PAYG | 2029-09-01 | 2004-09-28 | 2005-04-01 | Act | 2006-05-31 | 0 | 0 | 250000 | 250000
|  | Cap/Fin/Int | [5 empty] | 0 | 129764 | 1065000 | 1065000
| West Airfield Improvements | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2000-04-03 | Act | 2003-10-17 | 0 | 9112409 | 31906000 | 31906000
| Interconnect Re-route | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 1999-03-01 | Act | 2000-09-30 | 0 | 369055 | 1441000 | 1441000
| Taxiway Q Construction | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2001-06-25 | Act | 2002-04-25 | 0 | 1552756 | 4153000 | 4153000
| Runway 4R/22L Shoulders/Overburden (fka 3L/21R) | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2001-07-31 | Act | 2002-09-30 | 0 | 735822 | 2090000 | 2090000
| Deicing Pad at Runway 22L | Cap/Fin/Int | 2029-09-01 | 2004-09-28 | 2002-10-01 | Act | 2004-06-30 | 0 | 6601048 | 18123000 | 18123000
| Deicing Pads at Runway 4R and 3L | PAYG | 2029-09-01 | 2004-09-28 | 1998-08-01 | Act | 2000-09-30 | 0 | 2672000 | 2672000 | 2672000
|  | Cap/Fin/Int | [5 empty] | 0 | 6956871 | 37269000 | 37269000
| Perimeter Fencing and other Security Enhancements | PAYG | 2029-09-01 | 2004-09-28 | 2001-08-01 | Act | 2006-05-31 | 0 | 0 | 710000 | 710000
A086 | Surface Movement Guidance Control System | PAYG | 2029-09-01 | 2004-09-28 | 2004-11-01 | Act | 2005-12-01 | 0 | 0 | 1310000 | 1310000
A114 | Runway 3L/21R Planning | PAYG | 2029-09-01 | 2004-09-28 | 2005-10-01 | Est | 2015-12-31 | 0 | 0 | 700000 | 700000
A114 | Runway 3R/21L Design and Pavement Evaluation | PAYG | 2029-09-01 | 2004-09-28 | 2004-11-01 | Act | 2006-05-31 | 0 | 0 | 1200000 | 1200000
H001 | Part 150 Study Update | PAYG | 2029-09-01 | 2004-09-28 | 2003-10-01 | Act | 2009-09-30 | 0 | 326095 | 386156 | 386156
APPLICATION NO. 7
| Airfield Snow Removal Vehicles & Equipment | Cap/Fin/Int | 2032-10-01 | 2008-05-27 | 2002-05-01 | Act | 2008-06-30 | 0 | 1833188 | 16873119 | 16873119
MT891 | McNamara Terminal In-Line Explosive Detection | Cap/Fin/Int | 2032-10-01 | 2008-05-27 | 2006-11-01 | Act | 2010-01-05 | 0 | 4277033 | 110328130 | 110328130
A116 | Infill Island at Taxiway Y-10 | Cap/Fin/Int | 2032-10-01 | 2008-05-27 | 2005-10-01 | Act | 2006-03-31 | 0 | 85294 | 811236 | 811236
PL002 | Master Plan Update | Cap/Fin/Int | 2032-10-01 | 2008-05-27 | 2004-12-01 | Act | 2010-03-01 | 0 | 87823 | 946500 | 946500
A125 | Runway Surface Monitor System for RW 4L/22R | PAYG | 2032-10-01 | 2008-05-27 | 2010-02-01 | Est | 2014-09-30 | 0 |  | 1000000 | 1000000
| Runway and Taxiway Improvements | PAYG | 2034-02-01 | 2008-05-27 | 2005-10-01 | Est | 2014-11-30 | 0 | 1312000 | 1312000 | 1312000
|  | Cap/Fin/Int | [5 empty] | 0 | 1741440 | 96382583 | 96382583
[5 empty] | TOTAL USE APPROVAL |  |  | 14126316 | 1721449801.04 | 3134966084 | 3134966084
[5 empty] | TOTAL IMPOSE ONLY |  |  | 0 | 0 | 0 | 0
[5 empty] | GRAND TOTALS |  |  | 14126316 | 1721449801.04 | 3134966084 | 3134966084

## Annual Fcst
DETROIT METROPOLITAN WAYNE COUNTY AIRPORT
P.F.C. QUARTERLY STATUS REPORT
ANNUAL FORECAST FOR THE FISCAL YEAR ENDING 09/30/23
(1) | Total Estimated Enplaned Passengers | 16500000
(2) | Estimated Percent PFC Eligible | 86%
(3) | Total PFC Eligible Passengers | 14190000
(4) | PFC Amount per Passenger | 4.5
(5) | PFC Forecast Revenue - Total | 63855000
(6) | Estimated Collection Compensation | -1560900
(7) | Net to Public Agency | 62294100
Per FAA Regulations - Part 158, Subpart D, Section 63 (C)
Note on E11: Brian Pollack: Enplanement forecast based on draft Feasibility Report dated 5/4/21 (rounded down)